## Slide 1: SOMTech PMO
Definitions of Project Management Phases, Risks, Issues, & Change Management

## Slide 2: 4 Project Lifecycle Phases
INITIATION | PLANNING | EXECUTION & CONTROL | CLOSEOUT
Project concept created Identify key project stakeholders & objectives Project team identified and assigned Perform Rough Order of Magnitude (ROM) estimates Create Project Charter & submit for approval | Details of how to execute the project are built out Define high-level requirements Define change management strategy Perform high-level estimates Identify dependencies Create project schedule Develop communication plan Host project kickoff | Define detailed requirements Perform detailed estimates Manage communications and stakeholder engagement Further define project schedule as needed Implement on project deliverables Manage/assess project against schedule Document and monitor risks & issues Evaluate and calculate KPIs | Transition to operations Complete project documentation & archive Lessons Learned -review successes and failures to improve future projects Formal Acceptance
Project Management

## Slide 3: Project Risks
Risk: PMI defines a risk as “an uncertain event or condition that, if it occurs, has a positive or negative effect on a project's objectives”.
  Recommend using the if ―and ―then statement when documenting risks.
    For example, If X happens ―then the result will be Y.
Project Management

## Slide 4: Project Issues
Issue: An event or condition that has already happened and has impacted or is currently impacting the project objectives.
  Example: Delays in setting up the development and test environments are impacting the overall project schedule.
Project Management

## Slide 5: What is Change Management?
ITIL Change Management | Project Change Management | Prosci® Change Management
Designed to help control the life cycle of strategic, tactical, and operational changes to IT services through standardized procedures. Goal of Change Management is to control risk and minimize disruption to associated IT services and business operations. | The change control system to manage modifications to any formally controlled deliverable, project management plan component, or project document. | Prosci® is change management methodology implemented at VCU Health. The application of a structured process and set of tools for leading the people side of change to achieve a desired outcome (i.e. the people side of system, process and organizational changes).
Change Management